## Timeline
Event timeline
Enter your event date below. Every date in the plan, and the chart on the right, moves with it. Replace the starter tasks with your own. See the "How to use" sheet for a short guide.
Chart key
Event name | [5 empty] | Planned
Event date | 2027-05-15 |  |  |  |  | In progress
Venue | [5 empty] | Done
Organizer | [5 empty] | Event day
Days until the event | [7 empty] | Week by week (each column is the week beginning on the date shown)
[8 empty] | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | Event | +1 | +2
Task or milestone | Phase | Owner | Start date | Due date | Days to go | Status | Notes | 2027-01-30 | 2027-02-06 | 2027-02-13 | 2027-02-20 | 2027-02-27 | 2027-03-06 | 2027-03-13 | 2027-03-20 | 2027-03-27 | 2027-04-03 | 2027-04-10 | 2027-04-17 | 2027-04-24 | 2027-05-01 | 2027-05-08 | 2027-05-15 | 2027-05-22 | 2027-05-29
Set the goal, budget and guest numbers | Planning |  | 2027-01-23 | 2027-02-06 | 98 | Not started
Choose the date and shortlist venues | Planning |  | 2027-01-30 | 2027-02-13 | 91 | Not started
Book the venue | Booking |  | 2027-02-13 | 2027-02-20 | 84 | Not started
Book speakers, entertainment or hosts | Booking |  | 2027-02-20 | 2027-03-13 | 63 | Not started
Book catering and equipment | Booking |  | 2027-03-06 | 2027-03-27 | 49 | Not started
Open registration or send invitations | Promotion |  | 2027-03-13 | 2027-03-20 | 56 | Not started
Promote the event | Promotion |  | 2027-03-20 | 2027-05-08 | 7 | Not started
Confirm the schedule for the day | Logistics |  | 2027-04-10 | 2027-04-24 | 21 | Not started
Order signage, badges and printed materials | Logistics |  | 2027-04-17 | 2027-05-01 | 14 | Not started
Send final details to guests and suppliers | Event week |  | 2027-05-08 | 2027-05-12 | 3 | Not started
Brief the team and walk through the venue | Event week |  | 2027-05-13 | 2027-05-14 | 1 | Not started
Event day | Event week |  | 2027-05-15 | 2027-05-15 | 0 | Not started
Send thank-yous and a feedback survey | After the event |  | 2027-05-16 | 2027-05-18 | -3 | Not started
Review the budget and what to change next time | After the event |  | 2027-05-18 | 2027-05-25 | -10 | Not started
Progress
Not started | 14
In progress | 0
Done | 0
Overdue | 0
Free template from coavon.com/templates
Note on B5: Change this date and the whole plan moves with it.
Note on F10: Days between this task's due date and the event. A negative number is after the event.

## Event day schedule
Event day schedule
The running order for the day, hour by hour. Replace the example lines with your own.
Start | End | What is happening | Where | Who is leading | Notes
08:00 | 09:00 | Set up and supplier arrivals | Main hall
09:00 | 09:30 | Doors open and registration | Entrance
09:30 | 10:00 | Welcome | Main hall
10:00 | 12:00 | Main session | Main hall
12:00 | 13:00 | Lunch | Dining area
13:00 | 16:00 | Afternoon sessions
16:00 | 16:30 | Close and thank-yous | Main hall
16:30 | 18:00 | Pack down

## How to use
How to use this template
1. Enter the event date | Type your event date into the Event date box on the Timeline sheet. Every date in the plan is counted back from it, so the whole plan moves when it changes.
2. Make the tasks your own | Rename, delete or add tasks. The starter list covers a typical event; yours will differ.
3. Set the dates | Each starter date is a formula such as "event date minus 84 days". Change the number to move a task, or type a date over the formula.
4. Give every task an owner | One name per task. A task with two owners tends to be done by neither.
5. Read the chart | The colored bars on the right show when each task runs, week by week. Purple is planned, amber is in progress, green is done and black marks the event day.
6. Keep the status up to date | Choose Not started, In progress or Done. Finished tasks are crossed out and a late due date turns red.
7. Plan the day itself | Use the Event day schedule sheet for the running order, hour by hour.
Tip | Book the things that sell out first: the venue, then speakers or entertainment, then catering.