## Gantt chart
Gantt chart
Enter a start date and a length in days for each task. The end date and the bars on the right work themselves out. Phases (1, 2, 3...) take their dates from the tasks under them.
Key
Project |  | Website redesign |  |  |  | Phase
Project start |  | 2027-01-04 |  |  |  | Planned
Scroll the timeline (weeks) |  | 0 |  |  |  | Done
Today | [5 empty] | Milestone
Today
ID | Task | Owner | Start | Days | End | Progress | Notes
1 | Planning
1.1 | Kickoff meeting | Project lead |  | 1 |  | 100%
1.2 | Gather requirements | Project lead |  | 5 |  | 100% | Starts after 1.1
1.3 | Agree scope and budget | Sponsor |  | 2 |  | 50% | Starts after 1.2
1.4 | Plan approved | Sponsor |  | 0 |  | 0% | Starts after 1.3
2 | Design
2.1 | Sitemap and wireframes | Designer |  | 6 |  | 0% | Starts after 1.4
2.2 | Visual design | Designer |  | 8 |  | 0% | Starts after 2.1
2.3 | Design sign-off | Sponsor |  | 0 |  | 0% | Starts after 2.2
3 | Build
3.1 | Build the pages | Developer |  | 12 |  | 0% | Starts after 2.3
3.2 | Write and load content | Writer |  | 10 |  | 0% | Starts after 2.3
3.3 | Test and fix | Developer |  | 5 |  | 0% | Starts after 3.1
4 | Launch
4.1 | Go live | Project lead |  | 0 |  | 0% | Starts after 3.3
4.2 | Fix issues found after launch | Developer |  | 5 |  | 0% | Starts after 4.1
Free template from coavon.com/templates
Note on C5: The timeline starts on the Monday of this week.
Note on C6: Type 4 to move the timeline four weeks later. Use a negative number to go back.
Note on E11: Length in calendar days. 0 makes the task a milestone (a single black mark).
Note on G11: How much is done, from 0% to 100%. The done part of the bar turns dark.

## Bar chart method
Gantt chart: the stacked bar chart method
This table reads the tasks from the Gantt chart sheet. The chart is an ordinary stacked bar chart: the first series (the start date) is hidden, so only the duration shows as a bar.
Task | Start date | Duration (days)
A milestone (0 days) is drawn as a sliver 0.4 days long, so it still shows.
If you change the project start date, update the chart too: right-click the dates along the top, choose Format Axis, and set Minimum to the new start date (see the How to use sheet).

## How to use
How to use this Gantt chart template
1. Set the project start | On the Gantt chart sheet, type the date the project begins into Project start. The timeline begins on the Monday of that week.
2. List your tasks | Replace the example tasks with your own, one per row. Group them under phases (1, 2, 3) with tasks numbered 1.1, 1.2 and so on. A phase takes its dates from the tasks beneath it.
3. Enter start dates and lengths | Type a start date and a length in days for each task; the end date is worked out for you. To make a task start after another one finishes, type =F12+1 (using the row of the earlier task) as its start date. Several example tasks already do this.
4. Add milestones | Give a task a length of 0 days to make it a milestone: a single black mark on the day it happens.
5. Track progress | Type how much of each task is done, from 0% to 100%. The done part of the bar turns dark, and an end date that has passed on an unfinished task turns red.
6. Move the timeline | The timeline shows ten weeks. Type a number into Scroll the timeline (weeks) to move it later (or a negative number to move it earlier). Today's date is highlighted in yellow.
7. Add more rows | Copy a whole blank row and insert it where you need it. The bars and the end date formula come with it.
Bar chart method | The second sheet shows the same tasks as a classic Excel stacked bar chart. It updates when you change the tasks on the first sheet. If you change the project start date, right-click the dates on the chart, choose Format Axis, and set Minimum to the new start date.
Working days only | To count only Monday to Friday, change the End formula to =WORKDAY(D12,E12-1) and use =WORKDAY(F12,1) to start a task the next working day.